## ToDoList
To Do List
Project: 语音识别、机器翻译Python实现
Project / Task | Status | Priority | Due Date | Owner | Notes
理解语音识别、机器翻译大致原理 | Completed | - | 2018-05-15 | 全体小组成员
语音识别：分析例子代码大致结构与实现方式 | Completed | - | 2018-05-20 | 苏珊、杨若瑶 | 关注可以借鉴、参考的示例代码，可提取出来进行讨论
机器翻译：设计功能和大致代码模块 | Completed | - | 2018-05-22 | 朱莹、徐林源 | 根据讨论结果设计了大致的功能
语音识别：设计功能及其实现思路 | Completed | - | 2018-05-22 | 苏珊、杨若瑶
语音识别：小组讨论例子代码阅读心得 | Completed | - | 2018-05-25 | 苏珊、杨若瑶 | 逐行分析、精细阅读
语音识别：构建基础代码框架（类名、方法） | Completed | - | 2018-05-25 | 苏珊、杨若瑶 | 注意前后接口输出格式
机器翻译：阅读例子代码、更改设计构架 | Completed | - | 2018-05-30 | 朱莹、徐林源 | 根据参考例子代码，修改设计的框架
机器翻译：设计实现的类和方法 | Completed | - | 2018-05-31 | 朱莹、徐林源
语音识别：每人实现一个API调用 | Completed | - | 2018-06-01 | 苏珊、杨若瑶 | 关注每个API的功能特点及其参数要求
机器翻译：每人实现一个api调用 | Completed | - | 2018-06-08 | 朱莹、徐林源
机器翻译：根据语音识别部分，设置传参接口 | Completed | - | 2018-06-11 | 朱莹、徐林源 | 有待完善，api支持的语言需要调整
语音识别：整体功能封装成类 | Completed | - | 2018-06-11 | 苏珊、杨若瑶 | 实现初步功能，有待完善
语音识别：支持更多语言识别、支持更多API调用 | In Progress | - | 2018-06-16 | 苏珊、杨若瑶
机器翻译：api合并 | In Progress |  | 2018-06-18 | 朱莹、徐林源 | api需要调整并合并在一起
机器翻译：调整更多语言对 | In Progress | - | 2018-06-18 | 朱莹、徐林源 | 根据语音识别传参结果，增加更多语言对
语音识别：完善代码细节 | Planning |  | 2018-06-19 | 苏珊、杨若瑶
整理完善编码文档 | On Hold |  |  | 全体小组成员 | 统一格式、语言
撰写开发文档 | Planning |  |  | 全体小组成员

## Lists
Status | Priority | PICK
- | - | - | Edit these lists to change what shows up within the drop-down lists in the To Do List table.
Planning | high | Easy / Low Value
Pending Approval | normal | Easy / High Value
Approved | low | Hard / High Value
In Progress |  | Hard / Low Value
Pending Review
On Hold
Completed

## Help
HELP |  | © 2014 Vertex42.com
https://www.vertex42.com/ExcelTemplates/to-do-list-template.html
About
This to-do list was designed to be easy to customize. You can insert and delete columns as needed. To add more rows, just drag the table's drag handle in the lower right corner of the table.
Use the Lists worksheet to change what shows up in the drop-down lists in the Status, Priority, and PICK columns.
See the references below for more information about creating drop-down lists with data validation and named ranges.
Conditional Formatting
The Priority and Due Date columns use conditional formatting to highlight specific values. If you change the items in the Priority list, then you may need to edit the conditional formatting rule(s) as well.
When you select "Completed" from the status column, a conditional formatting rule makes the font in that row gray.
In the ToDoList worksheet, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit the rules.
PICK
The PICK column can be used to help you indicate the Difficulty (easy or hard) and Payoff Value (low or high) for a particular task. You can delete this column if you don't want to use it.
See the PICK Chart page on Vertex42.com for more information about this method.
Terms of Use
This spreadsheet, including all worksheets and associated content is considered a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
See License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this Help worksheet. If necessary, you may hide it by right-clicking on the Help tab and selecting Hide.
Additional Help
The link at the top of this worksheet will take you to the web page on vertex42.com that talks about this template.
REFERENCES
TIPS | Vertex42.com: Spreadsheet Tips Workbook
ARTICLE | Vertex42.com: PICK Chart
ARTICLE | Vertex42.com: Creating a Drop Down List via Data Validation
ARTICLE | Vertex42.com: Dynamic Named Ranges
Why this spreadsheet cannot be edited in Office for iPhone
- This worksheet uses the OFFSET function for dynamic named ranges
(work around: change the ranges to simple range references)
- Table formatting is not preserved, and you cannot edit values within Tables
(work around: convert the Tables to ranges)
- Conditional Formatting is not shown when viewing on the iPhone